## Iteration 2
BUG METRICS
S/N | Iteration | Function | Description | Cause | Action | Severity | Date found | Found By | Date Solved | Solved By | Current Score
1 | 2 | Login | Wrong username and password results in page crash | IndexOutOfBoundsException | Made changes to UserDAO | Low | 2015-10-10 | Wu Wei & Shu Wei | 2015-10-10 | Shu Wei & Wu Wei | 1
2 |  | Basic app break down by time usage | A blank page is shown. Suppose to redirect user back to Basic App Usage main page and display “No record shown” | The jsp page is not been redirected to the main page | Add code to redirect the user back to the welcome.jsp | High | 2015-10-10 | Jason & Jeremy | 2015-10-10 | Jason & Jeremy | 5
3 |  | Bootstrap | Gender is not case insensitive | The validation includes case sensitivity | Made changes to UserValidation | Low | 2015-10-10 | Wu Wei & Shu Wei | 2015-10-10 | Shu Wei & Wu Wei | 1
TOTAL SCORE = 2 x 1 (Low) + 1 x 5 (High) + 0 x 10 (Critical) = 7

## Iteration 3
BUG METRICS
S/N | Iteration | Function | Description | Cause | Action | Severity | Date found | Found By | Date Solved | Solved By | Current Score
1 | 3 | Basic Time Usage Report: Breakdown By Time Usage & Demographics | Records are not display accordingly when 3 or more categories are selected | Certain logics are not correctly implemented | Debug on servlet: BreakdownTimeDemoReport.java BreakdownTimeDemoUtility.java | Medium | 2015-10-24 | Jeremy & Yong Siang | 2015-10-24 | Shuwei and Jason | 5
2 |  | Smartphone Overuse Report | Different user has the same output results. The display of output results are incorrect as well | Certain logics are not correctly implemented | Debug on servlet: SmartphoneOveruseReport.java SmartphoneOveruseUtility.java | Medium | 2015-10-24 | Shuwei & Wu Wei | 2015-10-24 | Shuwei and Jason | 5
3 |  | Bootstrap | When using batch to insert data, there will be a BatchUpdateException thrown saying duplicate primary key.(But there is actually no duplication inside the data) | com.mysql.jdbc.exceptions.jdbc4.MySQLIntegrityConstraintViolationException | Debug on Model: AppUsageValidation.java LocationRecordValidation.java | Medium | 2015-10-24 | Shuwei & Wu Wei | 2015-10-24 | Shuwei and Jason | 5
TOTAL SCORE = 0 x 1 (Low) + 3 x 5 (High) + 0 x 10 (Critical) = 15

## Iteration 4
BUG METRICS
S/N | Iteration | Function | Description | Cause | Action | Severity | Date found | Found By | Date Solved | Solved By | Current Score
1 | 4 | Bootstrap | No output shown for number of rows added | Did not print | Debug bootstrap servlet | Medium | 2015-11-07 | Shu Wei & Jason | 2015-11-07 | Shu Wei & Jason | 5
2 |  | Basic App Usage | Breakdown by Usage Time incorrect output | Logic error | Debug breakdown by usage time servlet | Medium | 2015-11-07 | Jeremy & Wu Wei | 2015-11-07 | Jeremy & Wu Wei | 5
3 |  |  | Breakdown by Demographics incorrect output | Formatting error | Fix printing errors | Low | 2015-11-07 | Shu Wei & Jason | 2015-11-07 | Shu Wei & Jason | 1
4 |  |  | Breakdown by App Category incorrect output | Logic error | Debug app category servlet | Medium | 2015-11-07 | Jeremy & Wu Wei | 2015-11-07 | Jeremy & Wu Wei | 5
5 |  | Upload additional Data | No file chosen | Careless mistake | Fix typo error | High | 2015-11-07 | Yong Siang | 2015-11-07 | Shu Wei & Jason | 10
6 |  | Diurnal Pattern | Incorrect output | Logic error | Debug diurnal pattern servlet | Medium | 2015-11-07 | Shu Wei & Jason | 2015-11-07 | Shu Wei & Jason | 5
7 |  | Top-K App Usage | Incorrect output | Logic error | Debug Top-K app Usage servlet | Medium | 2015-11-07 | Yong Siang | 2015-11-07 | Shu Wei & Jason | 5
8 |  | User Interface | Some links are not working | Link to outdated jsp | Fix hyperlinks | Low | 2015-11-07 | Jeremy & Wu Wei | 2015-11-07 | Jeremy & Wu Wei | 1
9 |  | Smartphone Usage Heatmap | Results not sorted | Results stored in Hashmap | Sort output | Low | 2015-11-07 | Yong Siang | 2015-11-07 | Shu Wei & Jason | 1
10 |  | Social Activeness | Wrong output; percentage not in whole number | Logic error | Debug social activeness servlet | Medium | 2015-11-07 | Shu Wei & Jason | 2015-11-07 | Shu Wei & Jason | 5
[10 empty] | Total Score | 43

## Iteration 5
BUG METRICS
S/N | Iteration | Function | Description | Cause | Action | Severity | Date found | Found By | Date Solved | Solved By | Current Score
1 | 5 | Diurnal Pattern | Resuls for 22:00 and 23:00 are swapped | Iterator did not traverse in order when deployed to OpenShift | Debug Diurnal Pattern JSP page | Medium | 2015-11-15 | Shu Wei | 2015-11-15 | Yong Siang | 5
[10 empty] | Total Score | 5