## PPM
PAIR-PROGRAMMING METRICS (PPM)
S/N | Planned Start Date & Time | Planned End Date & Time | Actual Start Date & Time | Actual End Date & Time | Task/ Description | Actual Work Done/ Status | Coder 1 | Coder 2 | Estimated Duration | Actual Duration | Pair Programming Metric (Planned /Actual) | Action | PM Acknowledge
Iteration 1
1 | 2015-09-22 15:00 | 2015-09-22 16:00 | 2015-09-22 15:05 | 2015-09-22 15:55 | Coding for login, deploy on Openshift & debugging | new folders added: login.jsp, welcome.jsp, admin_login.jsp, admin_welcome.jsp | Yong Siang | Jason | 1 | 0.83333 | 0.90909 | No action required | Jeremy
2 | 2015-09-26 09:00 | 2015-09-26 12:00 | 2015-09-26 09:03 | 2015-09-26 12:47 |  | modified folders: login.jsp, admin_welcom.jsp | Yong Siang | Jason | 3 | 3.7333
3 | 2015-09-26 14:30 | 2015-09-26 15:00 | 2015-09-26 14:31 | 2015-09-26 14:54 |  | No modified folders, no bug is found | Jason | Jeremy | 0.5 | 0.38333
4 | 2015-09-26 08:45 | 2015-09-26 10:15 | 2015-09-26 08:39 | 2015-09-26 10:48 | Bootstrap Functionality development | new folders added: Bootstrap.java, ErrorMessage.java ,User.java, Admin.java, Dataprocess.java, UserDAO.java, ZipFileReader.java, uploadbean.jar, modified folders: admin_welcome.jsp | Shu Wei | Wu Wei | 1.5 | 2.15 | 0.72464 | 1. PM needs to investigate the causes of the deviation 2.Evaluate the subsequent pp tasks and re-estimate the hours | Jeremy
5 | 2015-09-26 13:00 | 2015-09-26 14:00 | 2015-09-26 12:56 | 2015-09-26 14:15 |  | modified folders: Dataprocess.java, Boostrap.java, ConnectionManager.java | Shu Wei | Yong Siang | 1 | 1.3
Iteration 2
6 | 2015-09-29 16:30 | 2015-09-29 17:30 | 2015-09-29 16:32 | 2015-09-29 18:02 | Validations for bootstrap and loading data into system database | new folders added: AppUsageValidation.java, AppValidation.java, UserValidation.java modified folders: Bootstrap.java | Shu Wei | Wu Wei | 1 | 1.5 | 0.86751 | PM needs to investigate the causes of the deviation | Wu Wei
7 | 2015-09-29 21:00 | 2015-09-29 22:00 | 2015-09-29 21:05 | 2015-09-29 22:25 |  | new folder added: LocationValidation.java, LocationDAO.java modified folders: Dataprocess.java | Shu Wei | Wu Wei | 1 | 1.32
8 | 2015-09-29 21:30 | 2015-09-29 22:15 | 2015-09-29 22:10 | 2015-09-29 22:31 |  | Create local SQL tables and test for loading data | Shu Wei | Wu Wei | 0.75 | 0.35
9 | 2015-10-03 12:30 | 2015-10-03 14:30 | 2015-10-03 12:27 | 2015-10-03 14:33 | Develop Basic App Usage Report | new folders added: basicAppUsage.jsp, basic-usage.jsp, breakdowanAppCategory.jsp, AppUsageUtility.java, App.java, AppDAO.java, AppUsage.java, AppUsageDAO.java | Yong Siang | Jason | 2 | 2.1 | 0.7773 | 1. PM needs to investigate the causes of the deviation 2.Evaluate the subsequent pp tasks and re-estimate the hours 3. Inform supervisor that we would reschedule for our pair programming for next functionality | Wu Wei
10 | 2015-10-06 13:30 | 2015-10-06 15:00 | 2015-10-06 13:11 | 2015-10-06 17:56 |  | new folders added: bdDemographics_process.java, AppUsageValidation.java modified folders: AppUsage.java, AppUsageDAO.java | Yong Siang | Jason | 1.5 | 4.73
11 | 2015-10-06 17:30 | 2015-10-06 19:30 | 2015-10-07 17:39 | 2015-10-07 19:45 |  | new folders added: LocationDAO.java, LocationRecord.java, BreakdownTimeDemoReport.java, BreakdownTimeDemoUtility.java modified folders: bdDemographics_process.java | Yong Siang | Jason | 2 | 2.08
12 | 2015-10-07 12:30 | 2015-10-07 20:15 | 2015-10-09 12:30 | 2015-10-09 14:38 |  | new folders added: diurnalPattern_process.jsp, diurnalPatternAppUsage.jspmodified folders: AppUsage.java, AppUsageDAO.java | Yong Siang | Jaspn | 2 | 2.13
13 | 2015-10-07 19:45 | 2015-10-07 21:15 | 2015-10-07 19:48 | 2015-10-07 21:00 |  | modified folders: bdAppCategory_process.jsp, AppUsageUtility.java,BreakdownTimeDemoUtility.java, | Yong Siang | Jason | 1.5 | 1.2
14 | 2015-10-12 11:15 | 2015-10-12 11:44 | 2015-10-12 11:15 | 2015-10-12 11:45 |  | Modified folders: BreakdownTimeDemoUtility.java | Yong Siang | Jason | 0.75 | 0.47
15 | 2015-10-07 03:15 | 2015-10-12 16:15 | 2015-10-12 14:57 | 2015-10-12 16:04 |  | Modified folders: BreakdownTimeDemoUtility.java | Yong Siang | Jason | 1 | 1.12
16 | 2015-10-03 20:15 | 2015-10-03 22:15 | 2015-10-03 20:17 | 2015-10-03 23:46 | Develop Top-k App Usage Report | new folders added: top-k.jsp, top-k-app-display.jsp, TopKAppReport.java | Shu Wei | Jeremy | 2 | 3.48 | 0.67985 | 1. PM needs to investigate the causes of the deviation 2.Evaluate the subsequent pp tasks and re-estimate the hours | Wu Wei
17 | 2015-10-05 13:00 | 2015-10-05 15:00 | 2015-10-05 13:00 | 2015-10-05 16:23 |  | new folders added: top-k-school-display.jsp, TopKSchoolReport.java modified folders: top-k.jsp | Shu Wei | Jeremy | 2 | 3.23
18 | 2015-10-07 12:30 | 2015-10-07 14:00 | 2015-10-07 12:32 | 2015-10-07 13:55 |  | new folders added: TopKStudentReport.java, top-k-student-display.jsp modified folders: top-k.jsp | Shu Wei | Jeremy | 1.5 | 1.38
Iteration 3
19 | 2015-10-13 16:30 | 2015-10-13 18:00 | 2015-10-13 16:31 | 2015-10-13 17:39 | Loading Location Data functionality | Develop Loading Location Data functionality(Upload file to database) | Shu Wei | Wu Wei | 1.5 | 1.12 | 1.6006 | No action required | Jason
20 | 2015-10-13 18:00 | 2015-10-13 20:00 | 2015-10-13 17:40 | 2015-10-13 18:29 |  | Develop Loading Location Data functionality (Validation for location.csv) and update previous bootstraps | Shu Wei | Wu Wei | 2 | 0.8 |  | Overestimated task's complexicity. Understand the function's complexity (whether if it can re-use codes), evaluate the subsequent pp tasks and re-estimate the hours
21 | 2015-10-15 18:00 | 15-10-15 19:30 | 2015-10-15 15:38 | 2015-10-15 15:38 |  | Develop Loading Location Data functionality (upload additional location data) | Shu Wei | Wu Wei | 1.5 | 1.72 |  | Bug in pplog.
22 | 2015-10-21 15:30 | 2015-10-21 17:30 | 2015-10-21 16:52 | 2015-10-21 18:52 |  | Develop Deletion of data using location-delete.csv | Shu Wei | Wu Wei | 2.5 | 2.07 |  | No action required
23 | 2015-10-21 19:00 | 2015-10-21 22:00 | 2015-10-21 18:58 | 2015-10-21 19:50 |  | Develop web UI for deletion of Data | Shu Wei | Wu Wei | 3 | 0.85 |  | Overestimated task's complexicity. Understand the function's complexity (Complicated logics involved), evaluate the subsequent pp tasks and re-estimate the hours
24 | 2015-10-23 15:30 | 2015-10-23 18:30 | 2015-10-23 15:29 | 2015-10-23 18:48 | Basic App Usage Report | Update requirement changes in Basic app usage report: Breakdown by Time Usage & Demographics | Jason | Shu Wei | 5 | 5.25 | 0.95238 | No action required | Jason
| 2015-10-24 10:30 | 2015-10-24 12:30 | 2015-10-24 10:40 | 2015-10-23 12:37
25 | 2015-10-24 14:00 | 2015-10-24 14:30 | 2015-10-24 13:54 | 2015-10-24 14:10 | Deployment, Integrating, Testing and Debugging | Deploy application to OpenShift | Jason | Wu Wei | 0.5 | 0.25 | 0.87041 | No action required | Jason
| 2015-10-24 14:45 | 24-10-15 15:45 | 2015-10-24 14:45 | 2015-10-24 15:29 |  | Integrating & testing with earlier functionalities | Jason | Wu Wei | 1 | 0.72
| 2015-10-24 14:45 | 2015-10-24 17:45 | 2015-10-24 14:44 | 24-10-15 18:57 |  | Testing & Debugging after deployment(if any test case failed) | Jason | Shu Wei | 3 | 4.2 |  | 3 bugs are found during testing. Complexicity of the bug is relatively high. Debugging completed, no further action required
26 | 2015-10-13 16:30 | 2015-10-13 19:30 | 13-10-15 17:39 | 2015-10-13 19:15 | Dual Interfaces (JSON API) | Develop Dual Interfaces functionality (Implement Json API for Login) | Yong Siang | Jeremy | 3 | 3.07 | 0.96657 | Bug in pplog. | Jason
27 | 2015-10-15 12:30 | 2015-10-15 15:15 | 2015-10-15 15:04 | 2015-10-15 15:04 |  | Develop Dual Interfaces functionality (Implement Json API for Basic app usage report) | Yong Siang | Jeremy | 2.75 | 2.92 |  | Bug in pplog.
| 2015-10-17 15:30 | 2015-10-17 16:45 | 2015-10-17 15:32 | 2015-10-17 16:51 |  |  |  |  | 1.25 | 1.32 |  | Continue on from 15 Oct. Current status imcomplete (75% completed). Carry on with other scheduled tasks, this function will be pushed to 22 Oct.
| 2015-10-22 12:30 | 2015-10-22 15:00 | 2015-10-22 12:25 | 2015-10-22 15:12 |  |  |  |  | 2.5 | 2.78 |  | Continue on from 17 Oct. Current status imcomplete (95% completed). Carry on with other scheduled tasks, this function will be pushed to buffer day. *REQUIREMENTS CHANGED* Basic App Usage Report: Breakdown by Time Usage & Demographics. Dual Interfaces (JSON API) willl be affected. Functionility will be pushed to the buffer day
28 | 2015-10-19 17:15 | 2015-10-19 21:15 | 2015-10-19 17:04 | 2015-10-19 20:47 |  | Develop Dual Interfaces functionality (Implement Json API for Top-K app usage report) | Yong Siang | Jeremy | 4 | 3.72 |  | No action required
29 | 2015-10-20 15:45 | 2015-10-20 18:45 | 2015-10-20 15:50 | 2015-10-20 19:09 |  | Develop Dual Interfaces functionality (Implement Json API for Smartphone Overuse report) | Yong Siang | Jeremy | 3 | 3.32 |  | Functionality has completed. However, there's still uncertainty with the logics. Discussion will be held on 22 Oct to resolve any changes if necessary before the clicking on the "complete" button in the pplog
30 | 2015-10-22 12:30 | 2015-10-22 15:00 | 2015-10-22 12:25 | 2015-10-22 15:12 |  | Develop Dual Interfaces functionality (Implement Json API for Basic app usage report) | Yong Siang | Jeremy | 2.5 | 2.78 |  | No action required
31 | 2015-10-22 12:30 | 2015-10-22 15:30 | 2015-10-22 12:27 | 2015-10-22 17:22 |  | Develop Dual Interfaces functionality (Implement Json API for Bootstrap) | Jason | Wu Wei | 5 | 4.92 |  | No action required
Iteration 4
32 | 2015-10-27 11:00 | 2015-10-27 16:00 | 27/10 11:24 | 2015-10-27 15:47 | Social Activeness Report Functionality | Develop Social Activeness Report (+JSON) | Jason | Shu Wei | 5 | 4.38 | 1.0359 |  | Yong Siang
33 | 2015-10-29 14:00 | 29/10 17:00 | 2015-10-29 14:00 | 2015-10-29 17:13 |  |  |  |  | 3 | 3.22 |  |  | Yong Siang
34 | 2015-10-31 12:00 | 2015-10-31 17:00 | 2015-10-31 13:09 | 2015-10-31 18:07 |  |  |  |  | 5 | 4.95 |  |  | Yong Siang
35 | 2015-10-27 16:00 | 27/10 18:00 | 2015-10-27 16:02 | 2015-10-27 18:03 | Basic app usage report | Update requirement changes in Basic app usage report: Diurnal Pattern | Jason | Yong Siang | 2 | 2.02 | 1.039 |  | Yong Siang
36 | 2015-10-29 12:00 | 2015-10-29 14:00 | 2015-10-29 12:07 | 2015-10-29 13:58 |  |  | Jason | Yong Siang | 2 | 1.83 |  |  | Yong Siang
37 | 2015-10-31 12:00 | 2015-10-31 15:00 | 2015-10-31 12:24 | 2015-10-31 15:59 | JSON (Bootstrap) | Requirements Update | Shu Wei | Jeremy | 3 | 3.57 | 0.84034 |  | Yong Siang
38 | 2015-11-02 15:30 | 2015-11-02 18:30 | 2015-11-02 15:46 | 2015-11-02 18:39 | JSON (Demographics) | Requirements Update | Shu Wei | Jason | 3 | 2.88 | 1.0417
39 | 2015-10-27 15:30 | 2015-10-27 19:30 | 2015-10-27 15:37 | 2015-10-27 20:10 | Smartphone Usage Heatmap functionality | Develop Smartphone Usage Heatmap | Jeremy | Wu Wei | 4 | 4.53 | 0.883 | No action required | Yong Siang
40 | 2015-10-29 12:00 | 2015-10-29 15:00 | 2015-10-29 12:21 | 2015-10-29 15:26 |  | Develop Dual Interfaces functionality (Implement Json API for Smartphone Usage Heatmap ) | Jeremy | Wu Wei | 3 | 3.08 | 0.97403 |  | Yong Siang
41 | 2015-11-03 13:15 | 2015-11-03 15:15 | 2015-11-03 13:13 | 2015-11-03 16:32 | Update Location Delete | Update Location Delete | Shu Wei | Jason | 2 | 2.32 | 0.86207 |  | Yong Siang
42 | 2015-11-03 15:30 | 03/11 18:30 | 2015-11-03 16:10 | 2015-11-03 19:20 | Propagate data back when error messages are shown for every functionality | Update required changes in previous function from supervisor's feedbacks | Jeremy | Wu Wei | 3 | 3.15 | 0.95238 |  | Yong Siang
43 | 2015-11-03 18:00 | 2015-11-03 21:00 | 2015-11-03 16:54 | 2015-11-03 23:10 | Testing & Debugging | Testing & Debugging after deployment(if any test case failed) | Yong Siang | Shu Wei | 3 | 6.25 | 0.48 | Plan longer sessions for debugging | Yong Siang
44 | 2015-11-03 19:00 | 2015-11-03 20:00 | 2015-11-04 18:35 | 2015-11-04 19:37 | Deployment | Deploy Application to OpenShift | Yong Siang | Shu Wei | 1 | 1.02 | 0.98039 |  | Yong Siang
45 | 03/11 19:45 | 2015-11-03 20:45 | 2015-11-04 19:38 | 2015-11-04 20:48 | Integration | Integrating and testing with earlier functionalities | Yong Siang | Shu Wei | 1 | 1.17 | 0.8547 |  | Yong Siang
46 | 2015-11-07 12:00 | 2015-11-07 14:00 | 2015-11-07 12:00 | 2015-11-07 13:59 | Testing & Debugging | Testing & Debugging after deployment(if any test case failed) | Yong Siang | Shu Wei | 2 | 1.97 | 1.0152 |  | Yong Siang
47 | 2015-11-07 12:30 | 07/11 18:30 | 2015-11-07 12:43 | 2015-11-07 18:57 |  | Improve app based on UAT Feedback | Jeremy | Wu Wei | 6 | 6.22 | 0.96463 |  | Yong Siang
Iteration 5
48 | P: 10/11 12:30 | 2015-11-10 14:30 | A: 10/11 12:45 - 10/11 15:00 |  | Debug the Social Activeness Report | Debug the Social Activeness Report | Shu Wei | Jason | 2 | 2.25 | 0.88889 |  | Shu Wei
49 | P: 10/11 12:30 | 2015-11-10 18:30 | A: 10/11 12:45 - 10/11 19:02 |  | Redo the diurnal pattern of app usage time | Redo the diurnal pattern of app usage time | Yong Siang | Wu Wei | 6 | 6.27 | 0.95694 |  | Shu Wei
50 | P: 10/11 16:15 | 2015-11-10 21:15 | A: 10/11 16:21 - 10/11 21:33 |  | Testing and debugging Json for all functions | Testing and debugging Json for all functions | Jeremy | Jason | 5 | 5.18 | 0.96525 |  | Shu Wei
51 | P: 10/11 18:30 | 2015-11-10 20:00 | A: 10/11 19:41 - 10/11 20:56 |  | Develop Json for diurnal pattern of app usage time | Develop Json for diurnal pattern of app usage time | Yong Siang | Wu Wei | 1.5 | 1.25 | 1.2 |  | Shu Wei
52 | P: 12/11 11:00 | 2015-11-12 11:30 | A: 12/11 13:17 - 12/11 14:19 |  | Update the error message display of Top-k | Update the error message display of Top-k | Shu Wei | Jeremy | 0.5 | 1.02 | 0.4902 | Underestimate task difficulty. Allocate more time for future tasks that are similar | Shu Wei
53 | P: 14/11 11:00 | 2015-11-14 16:00 | A: 14/11 11:40 - 14/11 16:47 |  | Check and update Javadoc and generate API for bootstrap, basic report, smartphone overuse report and top-k report | Check and update Javadoc and generate API for bootstrap, basic report, smartphone overuse report and top-k report | Wu Wei | Jeremy | 5 | 5.12 | 0.97656 |  | Shu Wei
54 | P: 14/11 16:15 | 2015-11-14 18:15 | A: 14/11 16:15 - 14/11 18:22 |  | Check and update Javadoc and generate API for heatmap and social activeness report | Check and update Javadoc and generate API for heatmap and social activeness report | Wu Wei | Yong Siang | 2 | 2.12 | 0.9434 |  | Shu Wei
55 | P: 14/11 16:45 | 2015-11-14 19:45 | A: 14/11 16:48 - 14/11 20:12 |  | Testing Json | Testing Json | Wu Wei | Jason | 3 | 3.4 | 0.88235 |  | Shu Wei
56 | P: 14/11 18:30 | 2015-11-14 21:30 | A: 14/11 18:29 - 14/11 22:01 |  | Testing all the functions in the project(web UI) and debugging(if there are any bugs) | Testing all the functions in the project(web UI) and debugging(if there are any bugs) | Shu Wei | Yong Siang | 3 | 3.52 | 0.85227 |  | Shu Wei
57 | P: 14/11 20:00 | 2015-11-14 22:00 | A: 14/11 20:14 - 14/11 22:14 |  | Updating web UI | Updating web UI | Jeremy | Jason | 2 | 1.98 | 1.0101 |  | Shu Wei
58 | P: 15/11 11:00 | 2015-11-15 14:00 | A: 14/11 22:05 - 15/11 01:36 |  | Deployment and debugging on OpenShift(if there are any bugs) | Deployment and debugging on OpenShift(if there are any bugs) | Wu Wei | Jeremy | 3 | 3.52 | 0.85227 |  | Shu Wei
End

## Sheet1
Debug the Social Activeness Report | WSWJJ | SMUX Grp Study Rm 3-2 | Debug the Social Activeness Report | P: 10/11 12:30 - 10/11 14:30 | A: 10/11 12:45 - 10/11 15:00 | P:2.00 H | A:2.25 H
P: 10/11 12:30 - 10/11 14:30 |  |  | Redo the diurnal pattern of app usage time | P: 10/11 12:30 - 10/11 18:30 | A: 10/11 12:45 - 10/11 19:02 | P:6.00 H | A:6.27 H
A: 10/11 12:45 - 10/11 15:00 |  |  | Testing and debugging Json for all functions | P: 10/11 16:15 - 10/11 21:15 | A: 10/11 16:21 - 10/11 21:33 | P:5.00 H | A:5.18 H
P:2.00 H |  |  | Develop Json for diurnal pattern of app usage time | P: 10/11 18:30 - 10/11 20:00 | A: 10/11 19:41 - 10/11 20:56 | P:1.50 H | A:1.25 H
A:2.25 H |  |  | Update the error message display of Top-k | P: 12/11 11:00 - 12/11 11:30 | A: 12/11 13:17 - 12/11 14:19 | P:0.50 H | A:1.02 H
84ac6f8abe |  |  | Check and update Javadoc and generate API for bootstrap, basic report, smartphone overuse report and top-k report | P: 14/11 11:00 - 14/11 16:00 | A: 14/11 11:40 - 14/11 16:47 | P:5.00 H | A:5.12 H
(Show All) | Completed | Undo Edit | Check and update Javadoc and generate API for heatmap and social activeness report | P: 14/11 16:15 - 14/11 18:15 | A: 14/11 16:15 - 14/11 18:22 | P:2.00 H | A:2.12 H
Redo the diurnal pattern of app usage time | WWTYS | SMUX Grp Study Rm 3-2 | Testing Json | P: 14/11 16:45 - 14/11 19:45 | A: 14/11 16:48 - 14/11 20:12 | P:3.00 H | A:3.40 H
P: 10/11 12:30 - 10/11 18:30 |  |  | Testing all the functions in the project(web UI) and debugging(if there are any bugs) | P: 14/11 18:30 - 14/11 21:30 | A: 14/11 18:29 - 14/11 22:01 | P:3.00 H | A:3.52 H
A: 10/11 12:45 - 10/11 19:02 |  |  | Updating web UI | P: 14/11 20:00 - 14/11 22:00 | A: 14/11 20:14 - 14/11 22:14 | P:2.00 H | A:1.98 H
P:6.00 H |  |  | Deployment and debugging on OpenShift(if there are any bugs) | P: 15/11 11:00 - 15/11 14:00 | A: 14/11 22:05 - 15/11 01:36 | P:3.00 H | A:3.52 H
A:6.27 H
97902e867b
(Show All) | Completed | Undo Edit
Testing and debugging Json for all functions | LTKWJJ | SMUX Grp Study Rm 3-2
P: 10/11 16:15 - 10/11 21:15
A: 10/11 16:21 - 10/11 21:33
P:5.00 H
A:5.18 H
7fa1a2e2d3
(Show All) | Completed | Undo Edit
Develop Json for diurnal pattern of app usage time | WWTYS | SMUX Grp Study Rm 3-2
P: 10/11 18:30 - 10/11 20:00
A: 10/11 19:41 - 10/11 20:56
P:1.50 H
A:1.25 H
40467f74b2
(Show All) | Completed | Undo Edit
Update the error message display of Top-k | WSLTK | SIS SR3-3
P: 12/11 11:00 - 12/11 11:30
A: 12/11 13:17 - 12/11 14:19
P:0.50 H
A:1.02 H
24b79eb8de
(Show All) | Completed | Undo Edit
Check and update Javadoc and generate API for bootstrap, basic report, smartphone overuse report and top-k report | WWLTK | SMUX Meeting Space
P: 14/11 11:00 - 14/11 16:00
A: 14/11 11:40 - 14/11 16:47
P:5.00 H
A:5.12 H
13ca2ba23f
(Show All) | Completed | Undo Edit
Check and update Javadoc and generate API for heatmap and social activeness report | WSTYS | SMUX Meeting Space
P: 14/11 16:15 - 14/11 18:15
A: 14/11 16:15 - 14/11 18:22
P:2.00 H
A:2.12 H
5fb1b10b71
(Show All) | Completed | Undo Edit
Testing Json | WWWJJ | SMUX Meeting Space
P: 14/11 16:45 - 14/11 19:45
A: 14/11 16:48 - 14/11 20:12
P:3.00 H
A:3.40 H
bd80f45413
(Show All) | Completed | Undo Edit
Testing all the functions in the project(web UI) and debugging(if there are any bugs) | WSTYS | SMUX Meeting Space
P: 14/11 18:30 - 14/11 21:30
A: 14/11 18:29 - 14/11 22:01
P:3.00 H
A:3.52 H
3e82413dd6
(Show All) | Completed | Undo Edit
Updating web UI | LTKWJJ | SMUX Meeting Space
P: 14/11 20:00 - 14/11 22:00
A: 14/11 20:14 - 14/11 22:14
P:2.00 H
A:1.98 H
d6eab7874b
Completed | Undo Edit
Deployment and debugging on OpenShift(if there are any bugs) | WWLTK | SMUX Meeting Space
P: 15/11 11:00 - 15/11 14:00
A: 14/11 22:05 - 15/11 01:36
P:3.00 H
A:3.52 H
622015e20c
(Show All) | Completed | Undo