## Sheet1
Task Metrics
Iteration | Tasks | Date Assigned | Completed? (Yes/No) | No. of Assigned Tasks (Planned) | No. of Completed Tasks (Actual) | TM Score: Actual/Planned (%) | Action
Start of Iteration 1
1 (PM: Jeremy) | Draw Diagrams(Use Case Scenarios/Class Diagrams) | 2015-09-15 | Yes | 17 | 17 | 100% | Our planning estimations are fairly accurate. No action is required.
| Write test cases for LOGIN | 2015-09-15 | Yes
| Write test plan | 2015-09-15 | Yes
| Discuss LOGIN functionality & draw diagrams(SD, LD) | 2015-09-18 | Yes
| Discuss & prepare slides for PM review | 2015-09-22 | Yes
| Discuss & prepare slides for supervisor meeting | 2015-09-22 | Yes
| Discuss BOOTSTRAP functionality and draw diagrams (SD, Class Diagrams) | 2015-09-22 | Yes
| Discuss and research about BOOTSTRAP functionality | 2015-09-22 | Yes
| Discuss and research about BOOTSTRAP functionality | 2015-09-22 | Yes
| Collect metrics & apply mitigations | 2015-09-26 | Yes
| Conduct Peer Sharing Session of codes | 2015-09-26 | Yes
| Deploy application to OpenShift | 2015-09-26 | Yes
| Develop BOOTSTRAP functionalities (drop table and test connection) | 2015-09-26 | Yes
| Develop BOOTSTRAP functionality(create csv reader, read files,upload zip & read zip) | 2015-09-26 | Yes
| PM Handover (Knowledge transfer on schedule, metrics, admin etc) | 2015-09-26 | Yes
| Testing & Debugging on Openshift (if any test case failed) | 2015-09-26 | Yes
| Update next iteration schedule (discuss next iteration tasks, schedule pp sessions,book venue etc) | 2015-09-26 | Yes
End of Iteration 1
Start of Iteration 2
2 (PM: Wu Wei) | Develop BOOTSTRAP functionality(creation and loading to sql table) | 2015-09-29 | Yes | 27 | 27 | 100% | Planning estimations are fairly accurate. No action is required.
| Develop BOOTSTRAP functionality (validation for demographics,app,app-lookup.csv) | 2015-09-29 | Yes
| Develop BOOTSTRAP functionality(creation and loading to sql table) | 2015-09-29 | Yes
| Write test cases for BASIC APP USAGE REPORT | 2015-09-29 | Yes
| Develop Top-K App Usage Report by most used apps | 2015-10-03 | Yes |  |  |  | Actual: 3.48 hrs Planned: 2hrs Delay: 1.48 hrs Reason: Not familiar with function, app duration calculation is complicated. We did not predict that the logic will be so complicated. Action: Both programmers coded over-time and managed to complete the function.
| Develop BASIC APP USAGE REPORT by time category | 2015-10-03 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Discuss BASIC APP USAGE REPORT functionality & Update Diagrams(SD/Class Diagrams) | 2015-10-03 | Yes
| Discuss Top-K App Usage Report functionality & Update Diagrams(SD/Class Diagrams) | 2015-10-03 | Yes
| Write test cases for Top-K App Usage Report | 2015-10-03 | Yes
| Develop Top-K App Usage Report by students with most app usage | 2015-10-05 | Yes |  |  |  | Actual: 3 hrs Planned: 2hrs Delay: 1hrs Reason: Met with bug after development, debugging has taken too long causing us to overshoot. Action: Both programmers coded over-time and managed to complete the function.
| Develop BASIC APP USAGE REPORT by time and demographic category | 2015-10-06 | Yes |  |  |  | Actual: 0 hrs Planned: 1.5 hrs Delay: 1.5 hrs Reason: Yong Siang was not able to make it due to involvement in AceTech 2015. Action: PP session will be pushed to 6/10/2015
| Develop Top-K App Usage Report by schools with most app usage | 2015-10-07 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Develop BASIC APP USAGE REPORT by diurnal pattern | 2015-10-07 | Yes
| Develop BASIC APP USAGE REPORT by app category | 2015-10-07 | Yes
| Develop Smartphone Overuse Report (Implement daily gaming duration metrics) | 2015-10-09 | Yes |  |  |  | Reason: Basic App Usage Report: Breakdown By Usage Time Category & Demographics is imcomplete. The pair-programmers (JASON & YONG SIANG) continue with Basic App Usage Report: Breakdown By Usage Time Category & Demographics Action: Smartphone Overuse Report is reassigned to another pair-programmers (SHUWEI & JEREMY).
| Develop Smartphone Overuse Report functionality (Implement daily smartphone usage duration metrics) | 2015-10-09 | Yes
| Develop Smartphone Overuse Report(Implement frequency of smartphone accesses metrics) | 2015-10-09 | Yes
| Discuss Smartphone overuse Report functionality & Update Diagrams(SD/Class Diagrams) | 2015-10-09 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Write Smartphone overuse Report test cases | 2015-10-09 | Yes
| Discuss Smartphone overuse Report functionality & Update Diagrams(SD/Class Diagrams) | 2015-10-09 | Yes
| Collect metrics & apply mitigations | 2015-10-10 | Yes
| Conduct Peer Sharing Session of codes | 2015-10-10 | Yes
| Deploy application to OpenShift | 2015-10-10 | Yes
| Integrating & testing with earlier functionalities | 2015-10-10 | Yes
| PM Handover (Knowledge transfer on schedule, metrics, admin etc) | 2015-10-10 | Yes
| Testing & Debugging after deployment (if any test case failed) | 2015-10-10 | Yes |  |  |  | Reason: Basic App Usage Report: Breakdown By Usage Time Category & Demographics is delayed. The pair-programmers (JASON & YONG SIANG) continue with Basic App Usage Report: Breakdown By Usage Time Category & Demographics during buffer day on 12 Oct. Action: Testing have not been conducted and will be done on the coming scheduled testing session on 24 Oct.
| Update next iteration schedule (discuss next iteration tasks, schedule pp sessions,book venue etc) | 2015-10-10 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
End of Iteration 2
Start of Iteration 3
3 (PM: Jason) | Develop Dual Interfaces functionality (Implement Json API for Basic app usage report) | 2015-10-13 | No | 26 | 25 | 96.15% | Actual: 7.02 hrs Planned: 3 hrs Delay: 9 days Reason: Unfamilair with JSON API and underestimated its complexicity. Action: Discuss among with the PM and assigned pairs. The pairs decided to code the functionality on 17-10-2015 and 22-10-2015) *REQUIREMENTS CHANGED* - Basic App Usage Report: Breakdown by Time Usage & Demographics. Action: Discuss among with the PM and assigned pairs. Another pairs (Jason & Shuwei) decided to code the functionality during buffer day on 26-10-2015
| Develop Loading Location Data functionality (Validation for location.csv) and update previous bootstraps | 2015-10-13 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Develop Loading Location Data functionality(Upload file to database) | 2015-10-13 | Yes
| Discuss Loading Location Data functionality | 2015-10-13 | Yes
| Discuss Dual Interfaces(Web UI and Web Services) | 2015-10-13 | Yes
| Generate and update Diagrams(SD/Class Diagrams) for Loading Location Data functionality. | 2015-10-13 | Yes
| Preparation for supervisor meeting | 2015-10-14 | Yes
| Develop Deletion of data using location-delete.csv | 15-10-2015 *Re-scheduled to 21-10-2015* | Yes |  |  |  | Actual: 2.07 hrs Planned: 2.5 hrs Delay: 6 days Reason: Bugs had occurred in PPLog. To prevent more issues arise due to the malfunction of PPLog, after discussion among the pairs and PM, the pairs decided to push the functionality to 21-10-2015. Action: Re-schedule the task to 21-10-2015 *Functionality completed on 21-10-2015 (No action required)
| Develop Loading Location Data functionality (upload additional location data) | 2015-10-15 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Discuss Deletion of data functionality | 2015-10-15 | Yes
| Dscussion on supervisor meeting | 2015-10-15 | Yes
| Generate and update Diagrams(SD/Class Diagrams) for Deletion of data functionality | 2015-10-15 | Yes
| Develop Dual Interfaces functionality (Implement Json API for Top-K usage report) | 2015-10-19 | Yes
| Develop Dual Interfaces functionality (Implement Json API for Smartphone overuse report) | 2015-10-20 | Yes |  |  |  | Actual: 3 hrs Planned: 3.32 hrs Delay: 2 days Reason: Functionality has completed on 20 Oct. However, there's still uncertainty with the logics and outputs. Action: Discussion will be held on 22 Oct to resolve any changes if necessary before the clicking on the "complete" button in the pplog
| Write test cases for Deletion of Data | 2015-10-20 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Write test cases for Loading Location Data | 2015-10-20 | Yes
| Develop web UI for deletion of Data | 2015-10-21 | Yes
| Develop Dual Interfaces functionality (Implement Json API for Login and Bootstrap) | 2015-10-22 | Yes |  |  |  | *REQUIREMENTS CHANGED* - Basic App Usage Report: Breakdown by Time Usage & Demographics - Bootstrap: Handling of columns in the bootstrap files & Performance Requirements Action: Requirement changes will affect the Dual Interfaces (JSON API for Bootstrap). Therefore. updating of these requirement changes will be forwarded to the next iteration (Iteration 4)
| Update requirement changes for Basic App Usage Report: Breakdown by Time Usage & Demographics and Bootstrap. | 2015-10-23 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Collect metrics & apply mitigations | 2015-10-24 | Yes
| Conduct Peer Sharing Session of codes | 2015-10-24 | Yes
| Deploy application to OpenShift | 2015-10-24 | Yes
| Integrating & testing with earlier functionalities | 2015-10-24 | Yes
| PM Handover (Knowledge transfer on schedule, metrics, admin etc) | 2015-10-24 | Yes
| Testing & Debugging after deployment (if any test case failed) | 2015-10-24 | Yes |  |  |  | Actual: 4.2 hrs Planned: 3.0 hrs Delay: 1.2 hrs Reason: 3 bugs are found during testing. Complexicity of the bug is relatively high. Action: All 3 bugs have resolved. The pairs coded over time.
| Update next iteration schedule (discuss next iteration tasks, schedule pp sessions,book venue etc) | 2015-10-24 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
End of Iteration 3
Start of Iteration 4
4 (PM: Yong Siang) | Develop Social Activeness Report | 2015-10-27 15:47 | Yes | 17 | 17 | 100% | Planning estimations are fairly accurate. No action is required.
| Develop Smartphone Usage Heatmap for app usage report | 2015-10-27 20:10 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Update Diurnal Pattern (Improve performance + include date selection) | 2015-10-27 18:03 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Update Diurnal Pattern (Improve performance + include date selection) | 2015-10-29 13:58 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| JSON for Smartphone Usage Heatmap | 2015-10-29 15:26 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Develop Social Activeness Report | 2015-10-29 17:13 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| JSON for Bootstrap (Requirements update!) | 2015-10-31 15:59 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Develop Social Activeness Report | 2015-10-31 18:07 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| JSON for Basic App Usage - Breakdown by Demographics (Requirement change) | 2015-11-02 18:39 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Update Location delete | 2015-11-03 16:32 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Propagate user input for forms | 2015-11-03 19:20 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Testing & Debugging after deployment(if any test case failed) | 2015-11-03 23:10 | Yes |  |  |  | OpenShift down. More bugs than expected - Redeploy and debug again the next day. PM's MacBook crashed and sent for repair
| Deploy application to OpenShift | 2015-11-04 19:37 | Yes |  |  |  | Deployment took shorter than expected. Everything went smoothly - Future deployment tasks to have shorter time
| Integrating & testing with earlier functionalities | 2015-11-04 20:48 | Yes |  |  |  | Debugging took longer than expected. Future debugging sessions to be longer
| Additional Testing & Debugging | 2015-11-04 18:58 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Testing & Debugging after deployment(if any test case failed) | 2015-11-07 13:59 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Improve application based on UAT feedback | 2015-11-07 12:43 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
End of Iteration 4
Start of Iteration 5
5 (PM: Shuwei) | Debug the Social Activeness Report | 2015-11-10 | Yes | 19 | 19 | 100% | Planning estimations are fairly accurate. No action is required.
| Develop Json for diurnal pattern of app usage time | 2015-11-10 | Yes
| Metrics Collection | 2015-11-10 | Yes
| Redo the diurnal pattern of app usage time | 2015-11-10 | Yes
| Testing and debugging Json for all functions | 2015-11-10 | Yes
| Update diagram of diurnal pattern of app usage time | 2015-11-10 | Yes
| Code sharing after redo the diurnal pattern of app usage time | 2015-11-12 | Yes
| Discuss the project management for final presentation | 2015-11-12 | Yes
| Prepare the slides for final presentation | 2015-11-12 | Yes
| Update the error message display of Top-k | 2015-11-12 | Yes |  |  |  | Actual: 0.5 hrs Planned: 1.02hrs Delay: 0.5hrs Reason: Met with bug during the updating of display Top-K error messages. Debugging has taken longer than expected, causing us to overshoot. Action: Both programmers coded over-time and managed to complete the function.
| Check and update Javadoc and generate API for bootstrap, basic report, smartphone overuse report and top-k report | 2015-11-14 | Yes |  |  |  | Planning estimations are fairly accurate. No action is required.
| Check and update Javadoc and generate API for heatmap and social activeness report | 2015-11-14 | Yes
| Deployment and debugging on OpenShift(if there are any bugs) | 2015-11-14 | Yes
| Testing Json | 2015-11-14 | Yes
| Testing all the functions in the project(web UI) and debugging(if there are any bugs) | 2015-11-14 | Yes
| Updating web UI | 2015-11-14 | Yes
| Finalise the all the directories in GIT | 2015-11-15 | Yes
| Finalize slides for presentation | 2015-11-15 | Yes
| Rehearsal for final presentation | 2015-11-17 | Yes
End of Iteration 5