## Slide 1: IS203 Software Engineering
G4-T6
Shu Wei
Yong Siang
Jason
Jeremy
Wu Wei(PM)
PM Review

## Slide 2: Overview
Functionalities
Schedule
Metrics
Role & responsibilities
Pair Programming

## Slide 3: Functionalities

## Slide 4
Team Colour = Cyan
Required Functionalities:
* Login
* Bootstrap
* Basic App Usage Report
* Top-k App Usage Report
* Smartphone Overuse Report
* Dual Interfaces
* Loading Location Data
* Deletion of Data
* Smartphone Usage Heatmap
* Social Activeness Report

## Slide 5
No functionalities would be dropped or added
Framework: Stick with Model View Controller (JSP Model 2)
No other frameworks will be using

## Slide 6: Schedule

## Slide 7: Iteration Schedule
5 Iterations:
Iteration 1: 14th September – 26th September (13 days)
Iteration 2: 26th September – 12th October (17 days)
Iteration 3: 12th October – 26th October (15 days)
Iteration 4: 26th October – 7th November (13 days)
Iteration 5: 7th November – 18th November (12 days)

## Slide 8: Why use Time Boxing?
Allow us to finish on time(Feature keeps pushing back time)
Easy for schedule rotation
Every Project Manager will have equal work distribution

## Slide 9: Timeline – an Overview
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Week 7 - 8
Week 5 - 6
Week 9 – 10
Week 11 - 12
Week 13 - 14
Project Progress
Time

## Slide 10: Iteration 1 (Week 5 - 6)
Project Planning and Scheduling
* Understand project requirements
* Break down functionalities to small tasks
* Develop schedules
Documentation
* Draft diagrams for Login and Bootstrap
* Amend Login diagrams based on code
Milestone Preparation
* Prepare slides for supervisor meeting
* Prepare slides for PM review

## Slide 11
Iteration 1 (Week 5 - 6)
Coding
* Login function
Integration & Testing
* Deployment through OpenShift
* Testing and Debugging
Collaborative Learning
* Conduct peer sharing sessions of codes
* Attend complimentary classes as a group
* Practice lab exercises together

## Slide 12
Iteration 1 (Week 5 - 6)
Iteration Review
* Schedule adjustment for next iteration
* Review, evaluation & feedback
* Review on supervisor’s feedback

## Slide 13
Iteration 2 (Week 7 - 8)
Documentation
* Draft diagrams for Basic App Usage Report, Top-k App Usage Report, Smartphone Overuse Report
* Amend diagrams based on code
Coding
* Bootstrap & Validation
* Basic App Usage Report
* Top-k App Usage Report
* Smartphone Overuse Report

## Slide 14
Iteration 2 (Week 7 - 8)
Milestone Preparation
* Update slides for PM Review
* Prepare slides for supervisor meeting 2
Integration & Testing
* Deployment through OpenShift
* Testing and Debugging

## Slide 15
Iteration 2 (Week 7 - 8)
Collaborative Learning
* Conduct peer sharing sessions of codes
* Attend complimentary classes as a group
* Practice lab exercises together
* Prepare lab test together
Iteration Review
* Schedule adjustment for next iteration
* Review, evaluation & feedback
* Review on PM review’s feedback

## Slide 16
Iteration 3 (Week 9 - 10)
Coding
* Dual Interfaces
* Loading Location Data
* Deletion of Data

## Slide 17
Iteration 4 (Week 11 - 12)
Coding
* Smartphone Usage Heatmap
* Social Activeness Report

## Slide 18
Iteration 4 (Week 11 - 12)
Collaborative Learning
* Conduct peer sharing sessions of codes
* Practice lab exercises together
* Conduct JSON API learnings
Iteration Review
* Schedule adjustment for next iteration
* Review, evaluation & feedback
* Review on supervisor’s feedback
* Review on UAT’s feedback

## Slide 19
Iteration 5 (Week 13 - 14)
Milestone Preparation
* Prepare slides for final presentation
* Meeting to have a few dry runs
* Wrap up all stuff and prepare for submission
Integration & Testing
* Deployment everything through OpenShift
* Testing and Debugging(if still have)
* Improve UI (user interface) & UE (user experience)

## Slide 20
Iteration 5 (Week 13 - 14)
Collaborative Learning
* Prepare final exam together
Iteration Review
* Reflection on the whole project
* Review, evaluation & feedback
* Review feedback on final presentation

## Slide 21: Buffer Time
In each iteration, we put two Sundays as our backup buffer time, thus we have two days of buffer within each iteration
For the whole project, we also reserve the first week of last iteration as buffer time, which is 7 days long

## Slide 22: Critical Path for Iteration 2 Week 7
Bootstrap Sequence Diagram Review
(1 day)
Finish Bootstrap Functionality Include All Validation
(5 days)
Debugging & Testing
(1 days)
Create SQL Tables & Update Diagrams
(2 days)
Code Sharing By Developers
(1 days)
Review Diagrams of Top-k App& Basic App Usage Report
(1 days)

## Slide 23: Critical Path for Iteration 2 Week 8
Coding of Top-k Usage Report Functionalities
(3 days)
Coding of Basic App Usage Report Functionalities
(3 days)
Code Review & Update Diagrams
(1 day)
Debugging & Deploy on OpenShift
(1 day)
Develop Smartphone Over-usage Report Functionalities
(3 days)
Iteration Review
(1 day)
Json Research & Self Learning
(3 day)

## Slide 24: Metrics

## Slide 25: Mitigation plan I
PAIR PROGRAMMING METRICS :
<50 -Increase time allocated to tasks in the next iteration (Need more time) -Review possible paring & estimation issues -OT to make up
50-150
  Go on with PP, no change
>150
  -Decrease time allocated to tasks in the next iteration (Overestimate) -Review possible paring & estimation issues

## Slide 26
Iteration Schedule Metrics |  |  |  |  | 
Iteration | % Completion | Estimated Days | Actual Days | Schedule Metric | Action
1 | 100% | 13 | 13 | 100% | No action required

## Slide 27: Mitigation plan II
SCHEDULE METRICS:
<90 -Inform supervisor within 24 hrs -Too slow/not finishing on schedule -OT to make up
90-110 Go on with Schedule, no change
>110 -Include more task in the next iteration (Overestimated time taken) -Add number of days gain to buffer

## Slide 28: Mitigation plan III
BUG METRICS:
<10 Use planned debugging time in the iteration
>10 Stop development and resolve the bug immediately PM reschedules the project

## Slide 29
S/N | ITERATION | FUNCTION | DESCRIPTION | CAUSE | CORRECTION MADE | SEVERITY | DATE FOUND | DATE SOLVED | Person FOUND | Pair SOLVED
BUG METRICS(To Do)

## Slide 30: Roles & responsibilities

## Slide 31: Project managers & Milestones
Week
6
7
9
11
12
14
Iteration | Week | Milestone | Project Manager
1 | 6 | Supervisor Meeting 1 | Jeremy
2 | 7 | PM Review | Wu Wei
3 | 9 | Supervisor Meeting 2 | Jason
4 | 11 | Supervisor Meeting 3 | Yong Siang
4 | 12 | User Acceptance Test | Yong Siang
5 | 14 | Final Presentation | Shu Wei
Iteration1
Iteration2
Iteration3
Iteration4
Iteration5

## Slide 32: Project Manager’s responsibilities
Responsibilities
1) Prepare agenda
2) Distribute Work equally to every member
3) Track all metrics
4) Prepare for milestone(s)
5) Lead internal group meetings
6) Find causes of deviations from PPLOG

## Slide 33: Coder’s responsibilities
Responsibilities
1) Build functionalities
2) Unique testing
3) Update PM of progress
4) Explain codes to other team members

## Slide 34: Meeting minutes taker
Role is rotating through this order:
Yong Siang
Jason
Wu Wei
Jeremy
Shu Wei
Responsibility: Update specific meeting minutes (with agenda, assignment of tasks and due date) and upload to GIT

## Slide 35: Pair Programming -rotation plan

## Slide 36: Coders/developers
Iteration | Functions | Coders
Iteration 1 | Login & Logout | Yong Siang & Jason
Iteration 2 | Bootstrap | Shu Wei & Wu Wei
 | Basic App Usage Report | Yong Siang & Jason
 | Top-k Usage Report | Shu Wei & Jeremy
 | Smartphone Overuse Report | Yong Siang & Jason
Iteration 3 | Dual Interfaces | Yong Siang & Jeremy
 | Loading Location Data | Shu Wei & Wu Wei
 | Deletion of Data | Wu Wei & Jeremy
Iteration 4 | Smartphone Usage Heatmap | Shu Wei & Jeremy
 | Social Activeness Report | Wu Wei & Jason
Iteration 5 | Improve UI & UE | 

## Slide 37: Pair rotation part I
Tasks | Assign to | Date
Login | Yong Siang & Jason | 22nd September
test connection | Yong Siang & Jason | 22nd September
Create csvReader, read files, upload zip & read zip | Shu Wei & Wu Wei | 26th September
Validation for demographics,app,app-lookup.csv | Shu Wei & Wu Wei | 29th September
Validation for location,location-lookup.csv | Shu Wei & Wu Wei | 29th September
Update and load data to SQL tables | Shu Wei & Wu Wei | 29th September
Usage report by time category | Yong Siang & Jason | 3rd October
Usage report by time and demographic category | Yong Siang & Jason | 6th October
Usage report by app category | Yong Siang & Jason | 7th October
Usage report of diurnal pattern | Yong Siang & Jason | 7th October

## Slide 38: Pair rotation part II
Tasks | Assign to | Date
Develop top-k most used apps | Shu Wei & Jeremy | 3rd October
Develop top-k students with most app usage | Shu Wei & Jeremy | 5th October
Develop top-k schools with most app usage | Shu Wei & Jeremy | 7th October
Implement daily smartphone usage duration metrics | Yong Siang & Jason | 9th October
Implement daily gaming duration metrics | Yong Siang & Jason | 9th October
Implement frequency of smartphone accesses metrics | Yong Siang & Jason | 9th October
Implement twitter bootstrap | Yong Siang & Jeremy | 13th October
Implement JSON API | Yong Siang & Jeremy | 17th October
Upload file | Shu Wei & Wu Wei | 13th October
Add file to database | Shu Wei & Wu Wei | 13th October

## Slide 39: Pair rotation part III
Tasks | Assign to | Date
Develop validation for location.csv | Shu Wei & Wu Wei | 17th October
Develop validation for location-lookup.csv | Shu Wei & Wu Wei | 17th October
Develop functionality to upload additional location data | Shu Wei & Wu Wei | 17th October
Develop deletion of data using location-delete.csv | Wu Wei & Jeremy | 20th October
Develop web UI for deletion of Data | Wu Wei & Jeremy | 22nd October
Develop Heatmap for app usage report | Shu Wei & Jeremy | 27th October
Develop social activeness report using online social communication activities | Wu Wei & Jason | 27th October
Develop social activeness report using physical grouping | Wu Wei & Jason | 29th October