## Slide 1: supervisor meeting 3
G4 - T6
IS203 - Software engineering
Tan Yong Siang (PM)
Wang Shu Wei
Jeremy Lee
Jason Wu
Wu Wei
30th Oct 2015

## Slide 2: agenda
Progress for past 2 weeks
Work distribution
Deviation(s) from planned schedule
Goal(s) & immediate milestone
Existing or potential problems
Metrics

## Slide 3: progress for past 2 weeks
Class Diagrams & Sequence Diagrams
Test Cases & Mitigation Plans
Peer sharing of codes
Project Administration
Coding
Loading Location Data
Dual Interface (JSON)
Deletion of Data
Adaptation to requirement changes
Integration & Deployment
Integrating and testing with previous functionalities
Deployment to OpenShift
Testing and debugging
Iteration 3
13 Oct - 24 Oct

## Slide 4: work distribution
Wang Shu Wei
Wu Wei
Tan Yong Siang
Jeremy Lee
Loading Location Data
Deletion of Data
Testing and debugging
Dual Interfaces (JSON) for all functionalities
Testing and debugging
Jason Wu
(Iteration 3 PM)
Jason Wu
Wu Wei
Class Diagrams & Sequence Diagrams
Test Cases, Mitigation Plans & Metrics
JSON for Bootstrap
Testing and debugging
Jason Wu
Wu Wei
Update requirement changes for Bootstrap & Basic App Report

## Slide 5: deviation from planned schedule
No deviation from planned schedule
All tasks completed on time
Currently halfway into Iteration (4)

## Slide 6: Goals for coming 2 weeks
1 | Social Activeness Report | Functionality Diagrams JSON Test Cases
2 | Update Diurnal Pattern | Include date selection option Improve performance
3 | Smartphone Overuse Report | Functionality Diagrams JSON Test Cases
4 | Update Requirement Changes | JSON - Basic App Usage (Demographics) JSON - Bootstrap
5 | Prepare for UAT | Deployment, Integration & Debugging Collect Metrics Prepare Mitigation

## Slide 7: immediate milestones
User Acceptance Test (UAT) (Week 12, In-Class) | Deploy application to OpenShift before 11:00pm, 4th November
Final Presentation (Week 14, In-Class) | 10 minutes for final presentation followed by 10-minutes Q & A.

## Slide 8: existing/potential problems
Diurnal Pattern function loading time can be shortened
UI needs improvement
Requirement changes causes adjustment and re-allocation of schedule
Possible further requirement changes

## Slide 9: project metrics
Chart: Task Metrics
| Iteration 1 | Iteration 2 | Iteration 3
Tasks Assigned | 17 | 27 | 26

## Slide 10: project metrics (detailed)
Iteration 3 | No. of Tasks Assigned (Planned) | No. of Tasks Completed (Actual) | Task Metric | Action
1 | 17 | 17 | 100% | No action required
2 | 27 | 27 | 100% | Re-estimate the duration of the tasks for future iterations
3 | 26 | 25 | 96.15% | No action required
Chart: 
| Iteration 1 | Iteration 2 | Iteration 3
Tasks Assigned | 17 | 27 | 26

## Slide 11: bug metrics
Chart: 
| Iteration 1 | Iteration 2 | Iteration 3
Score | 0 | 7 | 15

## Slide 12: bug metrics (detailed)
S/N | Function | Description | Cause | Action | Severity | Date Found | Found By | Date Solved | Solved By | Current Score
1 | Basic App Report: Breakdown by usage time category & demographics | Records are not display accordingly when 3 or more categories are selected | Logic error | Debug Servlets | High | 24/10/15 | Jeremy, Yong Siang | 24/10/15 | Shu Wei, Jason | 5
2 | Smartphone Overuse Report | Different users have the same output results. Outputs are incorrect. | Logic error | Debug Servlets | High | 24/10/15 | Shu Wei, Wu Wei | 24/10/15 | Shu Wei, Jason | 5
3 | Bootstrap | When using batch insert, BatchUpdateException thrown when there is no duplication | MySQLIntegrityConstraintViolationException | Debug Servlets | High | 24/10/15 | Shu Wei, Wu Wei | 24/10/15 | Shu Wei, Jason | 5
15
Chart: 
| Iteration 1 | Iteration 2 | Iteration 3
Score | 0 | 7 | 15

## Slide 13: pair programming metrics
Chart: Planned vs Actual (hours)
| Develop Loading Location Data | Develop Loading Location Data and update previous bootstraps | Develop Loading Location Data | Develop Deletion of data using location-delete.csv | Develop web UI for deletion of Data | Update requirement changes in Basic app usage report | Deploy application to OpenShift | Integrating & testing with earlier functionalities | Testing & Debugging after deployment
Planned | 1.5 | 2 | 1.5 | 2.5 | 3 | 5 | 0.5 | 1 | 3
Actual | 1.12 | 0.8 | 1.72 | 2.07 | 0.85 | 5.25 | 0.25 | 0.72 | 4.2

## Slide 14: pair programming metrics
Chart: PPM
| Develop Loading Location Data | Develop Loading Location Data and update previous bootstraps | Develop Loading Location Data | Develop Deletion of data using location-delete.csv | Develop web UI for deletion of Data | Update requirement changes in Basic app usage report | Deploy application to OpenShift | Integrating & testing with earlier functionalities | Testing & Debugging after deployment
PPM | 1.34 | 2.5 | 0.87 | 1.21 | 3.53 | 0.95 | 2 | 1.39 | 0.71

## Slide 15: pair programming metrics
Chart: PPM: Overall
| Coding for Login, Deploy on Openshift & Debugging | Bootstrap Functionality | Bootstrap validation, loading data | Basic App Usage Report | Top-k App Usage Report | Loading Location Data | Basic App Usage Report (Requirement changes) | Deployment, Integrating, Testing and Debugging | Dual Interfaces (JSON API)
PPM | 0.91 | 0.72 | 0.87 | 0.78 | 0.68 | 1.6 | 0.95238 | 0.87041 | 0.97

## Slide 16: thank you